## Sheet1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE DAYS | SPRINT
As a seller I want to list my new crop for auction so that the bidders can bid for my products and buy them #1000 | 5 |  |  |  | 1
Design the UI for the auction listing page. | 3 | Naveen | Completed | 4
Implement the form for sellers to input crop details (e.g.,name ,base price,image) | 1 | Naveen | Completed | 1
Validate the input fields to ensure all necessary information is provided. | 1 | Naveen | Completed | 1
As a seller I want to view the list of my crops and thier status so that I can track their status #1001 | 2 |  |  |  | 1
Implement a table to display crop details (e.g., name, base price,image) | 1 | Jeswanth | Completed | 1
Ensure the page is responsive and user-friendly. | 1 | Jeswanth | Completed | 1
As a seller view real time bids based on crops so that I know the current highest bid for the crop #1002 | 2 |  |  |  | 1
Implement a component to show the current all bids for each crop. | 1 | Begonia | Completed | 1
Ensure the display updates in real-time as new bids are placed. | 1 | Begonia | Completed | 1
As a seller I want to delete/update crop datails before bidding so that I can fix mistake and make updates #1003 | 2 |  |  |  | 1
Implement form validation to ensure updates are correct. | 1 | Vignesh | Completed | 1
Add confirmation dialogs for delete actions. | 1 | Vignesh | Completed | 1
As a seller I want to filter the crops by name so that it is easy to view the required Crops #1004 | 3 |  |  |  | 1
Implement the filtering logic to search and display crops based on the input name. | 2 | Jeswanth | Completed | 1
Ensure the filtering is efficient and responsive. | 1 | Jeswanth | Completed | 1
As a bidder I want to view list of available crops for auction so that I can buy the required crops #1005 | 3 |  |  |  | 1
Implement a table to show crop details (e.g., name, base price , image). | 2 | Begonia | Completed | 1
Ensure the page is responsive and user-friendly. | 1 | Begonia | Completed | 1
As a bidder I want to place bid on a crop so that I can participate in the auction #1006 | 3 |  |  |  | 1
Implement the form for bidders to input their bid amount. | 1 | Naveen | Completed | 1
Validate the input fields to ensure the bid is valid. | 2 | Naveen | Completed | 1
As a bidder I want to view the current highest bid so that it is easy for placing the next bid on the crop #1007 | 3 |  |  |  | 1
Implement a component to show the highest bid dynamically. | 2 | Nithis | In Progress | 1
Ensure the display updates in real-time as new bids are placed | 1 | Nithis | In Progress | 1
As a bidder I want to get notification if I won the bid so that I know the auction result #1008 | 2 |  |  |  | 1
Implement logic to determine the winning bid. | 1 | Naveen | In Progress | 1
Set up notifications for bidders when they win the bid. | 1 | Naveen | In Progress | 1
As a bidder I want to search crops by name so that I can easily find the crops #1009 | 2 |  |  |  | 1
Implement the search logic to find and display crops based on the input name. | 1 | Vignesh | In Progress | 1
Ensure the search is efficient and responsive. | 1 | Jeswanth | In Progress | 1
As an admin I want to view and approve crop listing so that the bidding will be completed.#1010 | 4 |  |  |  | 1
Implement a component to show pending crop listings. | 2 | Nithis | Not Started | 1
Add functionality for approving or rejecting listings. | 2 | Nithis | Not Started | 1
As an admin I want to view bidder/seller details so that I can know about the users #1011 | 3 |  |  |  | 1
Implement a table or list view to display user information (e.g., name, contact details, activity). | 2 | Begonia | Not Started | 1
Ensure the page is responsive and user-friendly. | 1 | Begonia | Not Started | 1
\
1011 | Admin | View bidder/Seller Details | Can know about the users