## Dashboard
Product Engineering _ RIX-2024 Batch1 Team
WBS¦PBI |  | Sprint-Review¦Retro |  | Sprint Capacity |  | Sprint 0 |  | Sprint 3
Sprint Backlog |  | Capacity Planning Sheet |  | Epic sheet |  | Sprint 1 |  | Sprint 4
Query Tracking Sheet |  | Action Item Sheet |  | Code Quality |  | Sprint 2 |  | Sprint 5
Team-1 |  | Team-2 |  | Team-3 |  | Team-4 |  | Team-5
Name | Role | Name | Role | Name | Role | Name | Role | Name | Role
Sandhiya | UI Developers | Mukesh | Back-end Developer | Rishi | Scrum Master | Vignesh | UI Developers | Arul Naveen | Tester
Terrance | Scrum Master | Kavya Sri | UI Developers | Vishweshwaran | UI Developers | Rajesh | Scrum Master | Tarun | Back-end Developer
Aashik | Back-end Developer | Nishanth | Tester | Nuttrenai | Back-end Developer | Jeswanth | Back-end Developer | Thangabalaji | UI Developers
Ranjithkumar Palanisamy | Tester | Arul Begonia Vincent | Scrum Master | Balaji Udayasankar | Tester | Nithis Bangaru Boopathiraj | Tester | Madhavan Ramalingam | Scrum Master

## WBS¦PBI
S.No. | PBI ( a.k.a Work-Item) | Duration Hrs | Status | Remarks
| Total Efforts (in Hrs) | 0 | Hours
| Total Efforts (in Days, if 3 hrs per day ) | 0 | Days

## Sprint-Backlog
Legend : | Sprint Status
Success :
Failure :
Sprint#1 | S.No. | User Story# | Work-Item / Task | Assigned to | Planned |  | Actual |  | Status | Remarks
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
| 1 | US-001 | Implement login for Admin | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 2 | US-002 | Enable Admin to reset user passwords | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 3 | US-003 | Create Admin dashboard for document review | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 4 | US-004 | View login analytics and user activity | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 5 | US-005 | Design customer registration form | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 6 | US-006 | Validate income field in registration | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 7 | US-007 | Design customer login form | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 8 | US-008 | Home page,Contact page,About us page | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 9 | US-009 | Customer Service Representative login page | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 10 | US-010 | Customer Service Representative dashboard for operations | Sandhiya | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 11 | US-011 | Admin login apis | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 12 | US-012 | Customer Registration page api | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 13 | US-013 | Customer login page api | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 14 | US-014 | Customer service representative registration api | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 15 | US-015 | Customer service representative login api | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 16 | US-016 | All the data must be stored in database | Aashik | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 17 | US-017 | Write testing test cases for frontend & backend | Ranjith | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
[8 empty] | Sprint Over All Status : | Success
Sprint#2 | S.No. | User Story# | Work-Item / Task | Assigned to | Planned |  | Actual |  | Status | Remarks
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
| 1 | User-201 | Design registration UI for Customer & CSR | Kavya Sri Vaipava Subramani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 2 | User-202 | Implement user type selection logic | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 3 | User-203 | Create customer registration form with validations | Kavya Sri Vaipava Subramani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 4 | User-204 | Enable document upload path(ID, address, income proof) | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 5 | User-205 | Admin dashboard for document review & approval | Kavya Sri Vaipava Subramani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 6 | User-206 | EMI card selection screen with card details | Kavya Sri Vaipava Subramani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 7 | User-207 | Activate EMI card post-payment | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 8 | User-208 | Implement form error handling & user feedback | Kavya Sri Vaipava Subramani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 9 | User-209 | Build document verification logic (OCR/Manual) | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 10 | User-210 | Create notification system (email/SMS) for approval status | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 11 | User-211 | Develop EMI card details API (limit, fee, type) | Mukesh Nagasamy | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 12 | User-212 | Write unit & integration tests for registration flow | Nisanth Saravanan | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 13 | User-213 | Bug Fixes & Final Review | Everyone | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
[8 empty] | Sprint Over All Status : | Success
Sprint#3 | S.No. | User Story# | Work-Item / Task | Assigned to | Planned |  | Actual |  | Status | Remarks
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
| 1 | US-301 | Design Product Catalog UI | Vishweshwaran Elangamani | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 2 | US-302 | EMI Calculator Component (Frontend) | Vishweshwaran Elangamani |  |  |  |  | Completed
| 3 | US-303 | EMI Calculator Logic (Backend) | Nuttrenai Vijayasankar |  |  |  |  | Completed
| 4 | US-304 | Purchase Flow Integration | Nuttrenai Vijayasankar |  |  |  |  | Completed | Validations need to be added
| 5 | US-305 | Purchase History Page (Frontend) | Vishweshwaran Elangamani |  |  |  |  | Completed | History with filters
| 6 | US-306 | Purchase History API | Nuttrenai Vijayasankar |  |  |  |  | Completed | API integrated
| 7 | US-307 | EMI Schedule Generation | Nuttrenai Vijayasankar |  |  |  |  | Completed | Monthly breakdown ready
| 8 | US-308 | EMI Schedule Display (Frontend) | Vishweshwaran Elangamani |  |  |  |  | Completed | UI with due dates
| 9 | US-309 | Manual Testing | Balaji Udayasankar |  |  |  |  | Completed | All test cases passed
| 10 | US-310 | Bug Fixes & Final Review | Everyone |  |  |  |  | Completed | Minor UI/logic fixes
[8 empty] | Sprint Over All Status : | Success
Sprint#4 | S.No. | User Story# | Work Item | Assigned to | Planned |  | Actual |  | Status | Remarks
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
| 1 | US-401 | Dashboard UI | Vignesh | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 2 | US-402 | EMI card usage details | Vignesh | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 3 | US-403 | EMI Tracking details for each purchased product | Vignesh | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 4 | US-404 | EMI card details | Jeswanth | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 5 | US-405 | Search products UI | Vignesh | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 6 | US-406 | Search products fetched from database | Jeswanth | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 7 | US-407 | Products EMI details | Jeswanth | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 8 | US-408 | Upcoming EMI display UI | Vignesh | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 9 | US-409 | Payment history API | Jeswanth | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 10 | US-410 | Manual testing | Nithis | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
| 11 | US-411 | Bug fixes and final review | Everyone | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | Completed
[8 empty] | Sprint Over All Status : | Success
Sprint#5 | [9 empty] | Remarks
| S.No. | User Story# | Work Item | Assigned to | Planned |  | Actual |  | Status
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
| 1 | ADMIN - 001 | Registration Approval UI | Thanga Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 2 | ADMIN - 002 | Registration Validation Logic | Tarun Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 3 | ADMIN - 003 | EMI Card Issuance Flow | Tarun Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 4 | ADMIN - 004 | Credit Limit Assignment UI | Thanga Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 5 | ADMIN - 005 | Product Listing Management | Thanga Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 6 | ADMIN - 006 | Purchase Tracking API | Tarun Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 7 | ADMIN - 007 | Revenue Analytics Dashboard | Thanga Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 8 | ADMIN - 008 | CSR Account Management | Madhavan | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 9 | ADMIN - 009 | CSR Chat Support Integration | Thanga Balaji | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 10 | ADMIN - 010 | Insurance Claim Framework (Placeholder) | Madhavan | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 11 | ADMIN - 011 | Mannual Testing | Arul Naveen | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
| 12 | ADMIN - 012 | Bug Fixes & Final Review | Everyone | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | In Progress
[6 empty] | Sprint Over All Status : | Success

## Sprint-Capacity
Sprint#1 (04-Dec-24 to 10-Dec-24) |  | Wednesday | Thursday | Friday | Monday | Tuesday
| Relevantz Hrs: | 4
Personal Hrs:
| Total Hrs (per day): | 4 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 4
Sprint#2 (12-Dec-24 to 18-Dec-24) |  | Thursday | Friday | Monday | Tuesday | Wednesday
| Relevantz Hrs: | 4
Personal Hrs:
| Total Hrs (per day): | 4 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 4
Sprint#3 |  | Friday | Monday | Tuesday | Wednesday | Thursday
| Relevantz Hrs: | 4
Personal Hrs:
| Total Hrs (per day): | 4 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 4
Sprint#4 |  | Friday | Monday | Tuesday | Wednesday | Thursday
| Relevantz Hrs: | 4
Personal Hrs:
| Total Hrs (per day): | 4 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 4
Sprint#5 |  | Friday | Monday | Tuesday | Wednesday | Thursday
| Relevantz Hrs: | 4
Personal Hrs:
| Total Hrs (per day): | 4 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 4
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Aneesh Pankajakshan May I know, why RelevantZ hours are less than 8 hours through out the sprint? Please check with him Reply: @Karthic Vethachalam Last week I spend almost a hour a day for the CAP training, since there is a deadline to complete it by December end. From this week onwards, I will plan the CAP training outside Relevantz hours.

## Sprint-Review¦Retro¦Actions
Sprint#1 | S.No. | Review Points |  | S.No. | Owner | Retro Points | S.No. | Action Items from Review / Retro | Owner | ETA | Status | Remarks
What Went-Well ?
| 1 |  |  | 1 |  |  | 1 | ?
| 2 |  |  | 2 |  |  | 2 | ?
| 3 |  |  | 3 |  |  | 3 | ?
| 4 |  |  | 4 |  |  | 4 | ?
| 5 |  |  | 5 |  |  | 5 | ?
What Went-Wrong ?
1
2
3
4
5
Sprint#2 | S.No. | Review Points | Responsible Person | S.No. |  | Retro Points | S.No. | Action Items from Review / Retro | Owner |  | Status | Remarks
What Went-Well ?
| 1 |  |  | 1 |  |  | 1
| 2 |  |  | 2 |  |  | 2
| 3 |  |  | 3 |  |  | 3
| 4 |  |  | 4 |  |  | 4
| 5 |  |  | 5
5
What Went-Wrong ?
| 1 |  |  | 1
| 2 |  |  | 2
| 3 |  |  | 3
| 4 |  |  | 4
| 5 |  |  | 5
Sprint#3 | S.No. | Review Points | Responsible Person | S.No. |  | Retro Points | S.No. | Action Items from Review / Retro | Owner |  | Status | Remarks
| 1 |  |  | 1 |  | What Went-Well ?
| 2 |  |  | 2 |  |  | 1
| 3 |  |  | 3 |  |  | 2
| 4 |  |  | 4 |  |  | 3
| 5 |  |  | 5 |  |  | 4
5
What Went-Wrong ?
| 1 |  |  | 1
| 2 |  |  | 2
| 3 |  |  | 3
| 4 |  |  | 4
| 5 |  |  | 5
Sprint#4 | S.No. | Review Points |  | S.No. | Owner | Retro Points | S.No. | Action Items from Review / Retro | Owner | ETA | Status | Remarks
What Went-Well ?
| 1 |  |  | 1 |  |  | 1 | ?
| 2 |  |  | 2 |  |  | 2 | ?
| 3 |  |  | 3 |  |  | 3 | ?
| 4 |  |  | 4 |  |  | 4 | ?
| 5 |  |  | 5 |  |  | 5 | ?
What Went-Wrong ?
1
2
3
4
5
Sprint#5 | S.No. | Review Points |  | S.No. | Owner | Retro Points | S.No. | Action Items from Review / Retro | Owner | ETA | Status | Remarks
What Went-Well ?
| 1 |  |  | 1 |  |  | 1 | ?
| 2 |  |  | 2 |  |  | 2 | ?
| 3 |  |  | 3 |  |  | 3 | ?
| 4 |  |  | 4 |  |  | 4 | ?
| 5 |  |  | 5 |  |  | 5 | ?
What Went-Wrong ?
1
2
3
4
5

## Datasheet
In Progress
Not Started
Completed
Carried

## Sprint 1
Product : Admin,Customer,Customer Representative Service Registration and login pages also home,contactus and aboutus page
Start Date : 5/9/2025
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Terrance | Module 1 | Scrum Master | Sprint 1 | 05-Sep to 05-Sep | Sprint Planning, Coordination, Review, Retro | 4 hrs | Completed | None
2 | Sandhiya |  | Frontend Developer |  | 05-Sep to 05-Sep | Design registration,login and dashboards UI for Customer and CSR |  | Completed | None
3 | Sandhiya |  | Frontend Developer |  | 05-Sep to 05-Sep | Create Admin,customer, CSR registration form with validations |  | Completed | None
4 | Sandhiya |  | Frontend Developer |  | 05-Sep to 05-Sep | Create Home,Contanct,About us pages |  | Completed | None
5 | Aashik |  | Backend Developer |  | 05-Sep to 05-Sep | Create Admin,customer,Csr login pages |  | Completed | None
6 | Aashik |  | Backend Developer |  | 05-Sep to 05-Sep | Connect that with apis |  | Completed | None
7 | Aashik |  | Backend Developer |  | 05-Sep to 05-Sep | CRUD operations should be performed |  | Completed | None
8 | Aashik |  | Backend Developer |  | 05-Sep to 05-Sep | Data should be stored |  | Completed | None
9 | Ranjith |  | Tester |  | 05-Sep to 05-Sep | Write unit test for Login and registration flows |  | Completed | None
10 | Ranjith |  | Tester |  | 05-Sep to 05-Sep | Bug Reporting & Final Verification |  | Completed | None

## Sprint 2
Product
Start Date
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Arul Begonia Vincent | Module 2 | Scrum Master | Sprint 2 | 05-Sep to 05-Sep | Sprint Planning, Coordination, Review, Retro | 4 hrs | Completed | None
2 | Kavya Sri Vaipava Subramani |  | Frontend Developer |  | 05-Sep to 05-Sep | Design registration UI for Customer and CSR |  | Completed | None
3 | Kavya Sri Vaipava Subramani |  |  |  | 05-Sep to 05-Sep | Create customer registration form with validations |  | Completed | None
4 | Kavya Sri Vaipava Subramani |  | Frontend Developer |  | 05-Sep to 05-Sep | EMI card selection screen with card details |  | Completed | None
5 | Mukesh Nagasamy |  | Backend Developer |  | 05-Sep to 05-Sep | Implement user type selection logic |  | Completed | None
6 | Mukesh Nagasamy |  | Backend Developer |  | 05-Sep to 05-Sep | Enable document upload path (ID, address, income proof) |  | Completed | None
7 | Nisanth Saravanan |  | Tester |  | 05-Sep to 05-Sep | Write unit test for registration flow |  | Completed | None
8 | Nisanth Saravanan |  | Tester |  | 05-Sep to 05-Sep | Bug Reporting & Final Verification |  | Completed | None

## Sprint 3
| Product | Finance Management System
| Start Date | 2025-09-05
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Rishi Kesava Vigneshver Manisekaran | Team 3 | Scrum Master | Sprint 3 | 05-Sep to 5-Sep | Sprint Planning, Coordination, Review, Retro | 4 hrs | Completed | None
2 | Vishweshwaran Elangamani |  | Frontend Developer |  |  | Product Catalog UI | 4 hrs | Completed | None
3 | Vishweshwaran Elangamani |  | Frontend Developer |  |  | EMI Calculator UI | 4 hrs | Completed | None
4 | Vishweshwaran Elangamani |  | Frontend Developer |  |  | Purchase History UI | 4 hrs | Completed | None
5 | Vishweshwaran Elangamani |  | Frontend Developer |  |  | EMI Schedule Display | 4 hrs | Completed | Minor UI alignment issue (fixed)
6 | Nuttrenai Vijayasankar |  | Backend Developer |  |  | EMI Calculator Logic | 4 hrs | Completed | None
7 | Nuttrenai Vijayasankar |  | Backend Developer |  |  | Purchase Flow Integration | 4 hrs | Completed | None
8 | Nuttrenai Vijayasankar |  | Backend Developer |  |  | Purchase History API | 4 hrs | Completed | None
9 | Nuttrenai Vijayasankar |  | Backend Developer |  |  | EMI Schedule Generation | 4 hrs | Completed | None
10 | Balaji Udayasankar |  | Tester |  |  | Manual Testing | 4 hrs | Completed | None
11 | Balaji Udayasankar |  | Tester |  |  | Bug Reporting & Final Verification | 4 hrs | Completed | Minor UI bugs (resolved)

## Sprint 4
| Product |  | Dashboard and Payment tracking
| Start Date |  | 2025-09-05
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Rajesh Valasubramanian | Team - 5 | Scrum Master | 4 | 9/5/2025 - 9/5/2025 | Sprint planning ,Coordination, Sprint retro | 4 | Completed | None
2 | Vignesh Babu Kumaran |  | Front end developer |  |  | Creating Dashboard |  | Completed | None
3 | [5 empty] | View overall purchased products |  | Completed | None
4 | [5 empty] | Check EMI details for individual products |  | Completed | Initially it didn't redirect to this page. Later resolved
5 | [5 empty] | View EMI card usage details |  | Completed | None
6 | [5 empty] | Upcoming EMI plan details |  | Completed | None
7 | Jeswanth Saravanamuniyandi |  | Backend Developer |  |  | Payment history details |  | Completed | None
8 | [5 empty] | Search products |  | Completed | None
9 | [5 empty] | User EMI card details |  | Completed | None
10 | [5 empty] | Payment status |  | Completed | None
11 | Nithis Bangaru Boopathiraj |  | Tester |  |  | Manual test case document |  | Completed | None

## Sprint 5
| Product |  | Admin Module
| Start Date |  | 2025-09-05
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Madhavan Ramalingam | Team - 5 | Scrum Master | 5 | 05/09/2025 to 05/09/2025 | Sprint Planning & Daily Standups, Sprint Review & Retrospective | 4 | Completed | None
2 | Thangabalaji Periya Karuppasamy |  | Frontend Developer |  |  | Design Admin Dashboard UI, Implement Credit Limit UI | 4 | Completed | None
3 | Tarun Balaji |  | Backend Developer |  |  | Develop EMI Card Issuance API, Revenue Tracking Logic | 4 | Completed | None
4 | Arul Naveen Arulthomas |  | Tester |  |  | Write Test Cases for EMI Flow, Regression Testing for Admin Module | 4 | Completed | None
5
6
7
8
9