## Dashboard
Mini Payroll Summary Dashboard SCRUM Book
Epic sheet | WBS¦PBI | Sprint Backlog | Sprint 1
Sprint Capacity | Sprint-Review¦Retro | Datasheet | Sprint 2
Product Backlog |  |  | Sprint 3

## WBS
S.No. | PBI ( a.k.a Work-Item) | Duration Hrs | Status | Remarks
<-- Back-end Developement -->
1 | Models, DTOs, Service Layer, and Utilities Implementation. | 3 | Completed
2 | Service Controller Implementations for Audit and Notifications. |  | Completed
<-- Controllers Implementation -->
3 | Authentication Capability Using JWT Bearer. | 16 | Completed
4 | Admin Controller Endpoints |  | Completed
5 | HR and HR Manager Endpoints |  | Completed
6 | Employee Endpoints |  | Completed
<-- Back-end QoL -->
7 | Back-end Quality of Life changes and Optimizations. |  | In Progress
<-- Front-end Developement -->
8 | WireFrame And Requirement Analysis | 4 | Completed
9 | API config and Route Planning |  | Completed
<-- Front-end Pages-->
10 | AuthContext, NavBar, Protected Routes configuration. | 30 | Completed
11 | Login |  | Completed
12 | Dashboard |  | Completed
13 | Audit Page - Admin + HR Manager |  | Completed
14 | Notification Page |  | Completed
15 | Admin - User List Page |  | Completed
16 | Employee List Page - HR + HR Manager |  | Completed
17 | CTC Form - HR + HR Manager |  | Completed
18 | Pay Slip Form - HR + HR Manager |  | Completed
19 | Exports Page - HR |  | Completed
20 | Approvals Page - HR Manager |  | Completed
21 | Analytics - HR Manager |  | Completed
22 | Profile Page - Employee |  | Completed
23 | Pay Slip List Page - Employee |  | Completed
24 | Pay Slip and CTC Compare Page - Employee |  | Completed
<-- Front-end QoL -->
25 | Front-end Quality of Life changes and Optimizations. |  | In Progress
| Total Efforts (in Hrs) | 50 | Hours

## PBI
USID | AS A… | SO THAT.. | Priority | Sprint | Status
US001 | As an Admin, I want to create skeletal user accounts for HR, HR Managers, and Employees, | so that they can later fill in their personal and professional details. | High | 1 | Completed
US002 | As an Admin, I want to reset passwords, | so that users can securely access the system. | Medium | 1 | Completed
US003 | As an Admin, I want to manage user account status, | so that users can be set to active and inactive status. | Medium | 1 | Completed
US004 | As an Admin, I want to remove a user account, | so that a user can no longer access the system. | Medium | 1 | Completed
US005 | As an Admin, I want to view and export audit logs, | so that they can be stored locally in my system for future use. | Low | 1 | Completed
US006 | As an HR or HR Manager, I want to fill in detailed CTC (Cost to Company) information for employees, | so that payroll data is accurate and reflects all salary components. | High | 1 | Completed
US007 | As an HR or HR Manager, I want to generate a pay slip based on the latest approved CTC, | so that the pay slip can be sent for approval and processed accurately. | High | 1 | Completed
US008 | As an HR, I want to generate and export pay slips in PDF and Excel format, | so that they can be used for compliance and audit purposes. | Medium | 1 | Completed
US009 | As an HR/HR manager, I want to view the employee list and select any employee, | so that I can generate and export their CTC and pay slip for payroll processing and audit purposes. | Medium | 1 | Completed
US010 | As an HR Manager, I want to review and approve CTC structures and pay slips submitted by HR | so that payroll is validated before release. | High | 1 | Completed
US011 | As an HR Manager, I want to release the approved pay slip, | so that the employees can get their pay slip. | High | 1 | Completed
US012 | As an HR Manager, I want to generate and export pay slips in PDF format, | so that they can be used for compliance and audit purposes. | Medium | 1 | Completed
US013 | As an HR Manager, I want to view and export audit logs, | so that they can be stored locally in my system for future use. | Low | 1 | Completed
US014 | As an HR Manager, I want to view payroll analytics including summaries, comparisons, and anomalies, | so that I can monitor payroll trends and detect irregularities. | Low | 1 | Completed
US015 | As an Employee, I want to view and update my contact information | so that my profile remains accurate and up to date. | Medium | 1 | Completed
US016 | As an Employee, I want to view my latest approved CTC breakdown, | so that I understand my salary structure. | High | 1 | Completed
US017 | As an Employee, I want to view and download my CTC history, | so that I can track changes and keep records. | High | 1 | Completed
US018 | As an Employee, I want to view and download my pay slips (Payslip Comparison), | so that I can track my earnings and maintain records. | Low | 1 | Completed
US019 | As a User, I want to reset my password, | so that I can access my account. | Medium | 1 | Completed
US020 | As a User, I want to log in securely, | so that I can access my dashboard. | Medium | 1 | Completed
US021 | As a User, I want to receive notifications, | so that I can be updated on any action with respect to me. | Low | 1 | Completed

## Sprint-Backlog
Legend : | Sprint Status
Success :
Failure :
Sprint#1 | S.No. | User Story# | Work-Item / Task | Assigned to | Planned |  | Actual |  | Status | Remarks
[5 empty] | Start Date | End Date | Actual Start Date | Actual End Date
<-- Back-end Developement -->
| 1 | - | Models, DTOs, Service Layer, and Utilities Implementation. | Nisanth | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-13 | Completed
| 2 | US005 US008 US012 US013 US018 US021 | Service Controller Implementations for Audit and Notifications. | Nisanth | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-13 | Completed
<-- Controllers Implementation -->
| 3 | US002 US020 US019 | Authentication Capability Using JWT Bearer. | Nisanth | 2025-09-12 | 2025-09-14 | 2025-09-12 | 2025-09-14 | Completed
| 4 | US001 US002 US003 US004 US005 | Admin Controller Endpoints | Nisanth | 2025-09-12 | 2025-09-14 | 2025-09-12 | 2025-09-14 | Completed
| 5 | US006 US007 US008 US009 US010 US011 US012 US013 US014 | HR and HR Manager Endpoints | Nisanth | 2025-09-12 | 2025-09-14 | 2025-09-12 | 2025-09-14 | Completed
| 6 | US015 US016 US017 US018 | Employee Endpoints | Nisanth | 2025-09-12 | 2025-09-14 | 2025-09-12 | 2025-09-14 | Completed
<-- Back-end QoL -->
| 7 | - | Back-end Quality of Life changes and Optimizations. | Nisanth | 2025-09-12 | None | 2025-09-12 | None | In Progress
<-- Front-end Developement -->
| 8 | - | WireFrame And Requirement Analysis | Nisanth | 2025-09-12 | 2025-09-13 | 2025-09-12 | 2025-09-13 | Completed
| 9 | - | API config and Route Planning | Nisanth | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | Completed
<-- Front-end Pages-->
| 10 | US002 US020 US019 | AuthContext, NavBar, Protected Routes configuration. | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 11 | US002 US020 US019 | Login | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 12 | - | Dashboard | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 13 | US005 US013 | Audit Page - Admin + HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 14 | US021 | Notification Page | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 15 | US001 US002 US003 US004 | Admin - User List Page | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 16 | US009 | Employee List Page - HR + HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 17 | US006 | CTC Form - HR + HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-18 | Completed
| 18 | US007 | Pay Slip Form - HR + HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-18 | Completed
| 19 | US008 | Exports Page - HR | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 20 | US010 US011 US012 | Approvals Page - HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-18 | Completed
| 21 | US014 | Analytics - HR Manager | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 |  | Completed
| 22 | US015 US016 US017 | Profile Page - Employee | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 23 | US018 | Pay Slip List Page - Employee | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 | 2025-09-16 | Completed
| 24 | US018 | Pay Slip and CTC Compare Page - Employee | Nisanth | 2025-09-13 | 2025-09-16 | 2025-09-13 |  | Completed
<-- Front-end QoL -->
| 25 | - | Front-end Quality of Life changes and Optimizations. | Nisanth | 2025-09-13 | None | 2025-09-13 | None | In Progress
Sprint Over All Status :
Note on C2: Karthic Vethachalam: @Gowtham Sridharan Please make the sheet handy by formatting all the sheets neatly

## Sprint-Review¦Retro¦Actions
Sprint#3 | S.No. | Review Points |  | S.No. | Owner | Retro Points | S.No. | Action Items from Review / Retro | Owner | ETA | Status | Remarks
What Went-Well ?
| 1 |  |  | 1 |  |  | 1 | ?
| 2 |  |  | 2 |  |  | 2 | ?
| 3 |  |  | 3 |  |  | 3 | ?
| 4 |  |  | 4 |  |  | 4 | ?
| 5 |  |  | 5 |  |  | 5 | ?
6
| 7 |  |  |  |  | What Went-Wrong ?
1
2
3
4
5
Late code integration
Sprint#4 | S.No. | Review Points | Responsible Person | S.No. |  | ? | S.No. | Action Items from Review / Retro | Owner |  | Status | Remarks
| 1 |  |  |  |  | Retro Points | 1
| 2 |  |  |  |  | What Went-Well ? | 2
| 3 |  |  | 1 |  |  | 3
| 4 | [5 empty] | 4
| 5 |  |  | 3 |  |  | 5
| 6 |  |  | 4
| 7 |  |  | 5
8
| 9 |  |  |  |  | What Went-Wrong ?
| 10 |  |  | 1
| 11 |  |  | 2
| 12 |  |  | 3
4
5
Sprint#5 | S.No. | Review Points | Responsible Person | S.No. |  | ? | S.No. | Action Items from Review / Retro | Owner |  | Status | Remarks
| 1 |  |  |  |  | Retro Points | 1
| 2 |  |  |  |  | What Went-Well ? | 2
| 3 | [5 empty] | 3
| 4 | [5 empty] | 4
| 5 | [5 empty] | 5
What Went-Wrong ?

## Sprint-Capacity
Sprint#1 (10/09/2025 - 17/09/2025) |  | Wednesday | Thursday | Friday | Monday | Tuesday
| Relevantz Hrs: | 4 | 4 | 4 | 8 | 8
| Personal Hrs: | 4 | 4 | 5 | 5 | 4
| Total Hrs (per day): | 8 | 8 | 9 | 13 | 12
| Total Hrs (per Sprint): | 50
Relevantz Hrs:
Personal Hrs:
| Total Hrs (per day): | 0 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 0
Relevantz Hrs:
Personal Hrs:
| Total Hrs (per day): | 0 | 0 | 0 | 0 | 0
| Total Hrs (per Sprint): | 0

## Datasheet
STATUS | PRIORITY
In Progress | High
Not Started | Medium
Completed | Low
Carried

## Sprint 1
| Product | Mini Pay Roll Summary Dashboard.
| Start Date | 2025-10-09
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 | Nisanth Saravanan | - | SCRUM Master | 1 | 5 Business Days 10/9/2025 - 17/9/2025 | Sprint Planning, Coordination, Review, Retro | 50 | In Progress
2 | Nisanth Saravanan |  | Back End Developer |  |  | Create a comprehenside ASP .NET Web API for the application. |  | In Progress
3 | Nisanth Saravanan |  | Front End Developer |  |  | Create a comprehenside React JS (CRA) front-end application. |  | In Progress
4 | Nisanth Saravanan |  | Tester and QA |  |  | Test the functionalities of the API and the front-end by Unit Testing and Mannual Testing. Perform automated testing. Use tools like SonarQube for QA analysis. |  | Not Started
5 | Nisanth Saravanan |  | DevOps |  |  | Deploy in Docker. Deploy as a Jenkins Pipeline. Deploy in Cloud (Optional) |  | Not Started
6
7
8
9

## Sprint 2
Product
Start Date
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 |  |  |  | 2
2
3
4
5
6
7
8
9

## Sprint 3
Product
Start Date
# | Name | Team Name | Role | Sprint # | Sprint Duration | Task | Estimated Hours | Status | Impediments
1 |  |  |  | 3
2
3
4
5
6
7
8
9