## User story
USER STORIES
MODULE: PRODUCT COMPARISON & SHOPPING CART
ID | USER STORY | ACCEPTANCE CRITERIA
101 | As a user, I want to add products to my shopping cart so that I can purchase them later. | User can add a product to the cart from the product page. The cart icon updates to reflect the number of items added. A confirmation message is shown after adding a product.
102 | As a user, I want to update the quantity of products in my cart using plus and minus buttons so that I can adjust my order. | Plus and minus buttons are available for each product in the cart. Quantity updates immediately when buttons are clicked. Total price updates automatically based on quantity. Quantity cannot be less than 1.
103 | As a user, I want to proceed to checkout from the cart so that I can complete my purchase. | A “Proceed to Checkout” button is available in the cart. Clicking the button navigates the user to the checkout page. Only products with quantity ≥ 1 are included in the checkout.
104 | As a user, I want to view all products added to my cart so that I can review my selections before purchasing. | Cart displays all added products with name, image, price, and quantity. Cart is accessible from any page via a cart icon or link. Cart updates dynamically when products are added or removed.
105 | As a user, I want to remove products from my cart so that I can change my purchase decision. | Each product in the cart has a remove/delete option. Upon removal, the product is no longer listed in the cart. Total price updates after removal.
106 | As a user, I want to see the total price of all items in my cart so that I can understand the cost before checkout. | Cart displays subtotal, taxes (if applicable), and total price. Total price updates automatically when quantity changes or items are removed.
107 | As a user, I want my cart items to persist across sessions so that I don’t lose my selections when I return later. | Cart items are saved for logged-in users. Cart is restored when the user logs back in. Guest users may have temporary cart storage via cookies/session.
108 | As a user, I want to add products to a comparison list so that I can evaluate multiple products side-by-side before making a purchase. | User can add a product to the comparison list from the search results, home page, product page, or compare page. A maximum of 4 products can be added to the comparison list. If 4 products are already added, the system should prevent adding a fifth product and show a message. Products added to the comparison list should be displayed in a comparison view with key attributes. User can remove any product from the comparison list.
109 | As a user, I want to remove products from the comparison list so that I can refine my selection. | Each product in the comparison list has a remove option. Upon removal, the product is no longer shown in the comparison view. The comparison view updates dynamically after removal.
110 | As a user, I want to view comparison of selected products so that I can easily evaluate their features and differences. | Comparison page displays selected products in a list/grid format. Key attributes (e.g., price, brand, specifications) are shown for each product. Differences between products are highlighted visually.
111 | As a user, I want to be notified when I try to add more than 4 products to the comparison list so that I understand the limit. | System prevents adding a fifth product to the comparison list.
112 | As a user, I want the comparison list to persist while I navigate the site so that I don’t lose my selected products. | Comparison list is retained across pages during the session. Products remain in the list until manually removed or session expires. Logged-in users have persistent comparison lists across sessions.
113 | As a user, I want to clear all products from the comparison list at once so that I can start a new comparison easily. | A “Clear All” button is available on the comparison page. Clicking the button removes all products from the list. Comparison view resets to empty state.
114 | As a user, I want to see product images and links in the comparison view so that I can quickly access detailed product pages. | Each product in the comparison view includes an image and a clickable link. Clicking the link navigates to the product detail page. Images are displayed in consistent size and format.
115 | As a user, I want to compare products based on attributes relevant to the price so that the comparison is meaningful. | Only price attributes are shown for each product type. Attribute labels are clear and consistent.
116 | As a user, I want to search for products using keywords so that I can quickly find items I’m interested in. | A search bar is available on all major pages (e.g., home, category, header). User can enter keywords to search for products. Search results display relevant products based on the entered keywords. Results include product name, image, price, and link to product page. If no results are found, a message is displayed with suggestions or alternatives.

## Product-Backlog
PRODUCT BACKLOG INSURANCE MODULE
MODULE: PRODUCT COMPARISON & SHOPPING CART
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
101 | User | Add a product to the cart. | I can checkout the cart at a later point of time. | High | 1 | Complete | Not Started | High
102 | User | Increase and decrease the quantity of the product in the cart. | I can have the desirable amount of the product in the cart. | Medium | 1 | Complete | In Progress | Medium
103 | User | Remove a product from the cart. | I can remove unwanted product from the cart at a later point of time. | High | 1 | Complete | Complete | Low
104 | User | Search for a product in the cart. | I can filter out and find the product in my cart. | Low | 1 | Not Started | Overdue
105 | User | View the subtotal. | I can know prior to the checkout my bill without taxes. | Medium | 1 | Complete
106 | User | Proceed to Checkout. | I can pay for my product and request for delivery. | High | 1 | In Progress | On Hold
107 | User | Add a product to the comparison list. | I can compare any 4 products I desire. | Medium | 1 | Complete
108 | User | Remove a product to the comparison list. | I can change the products to compare freely. | Medium | 1 | Complete
109 | User | Search for a product. | I can filter out and find the product I desire. | Low | 1 | In Progress
TOTAL |  |  |  |  | 9

## Sprint-Backlog
AGILE SPRINT BACKLOG INSURANCE MODULE WITH BURNDOWN CHART
MODULE: PRODUCT COMPARISON & SHOPPING CART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint-Review
SPRINT REVIEW
MODULE: PRODUCT COMPARISON & SHOPPING CART
S.NO. | COMMENT | PERSON RESPONSIBLE

## Sprint_Retrospective
SPRINT RETROSPECTIVE
MODULE: PRODUCT COMPARISON & SHOPPING CART
S.NO. | WHAT WENT WELL? | WHAT WENT WRONG?