## Sheet1
PRODUCT BACKLOG INSURANCE MODULE
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
101 | As a farmer. | I want to fill an online insurance application form with my crop and bank details. | so that I can avail crop insurance under the government scheme. | High | 1 | Complete | Not Started | High
102 | As a farmer. | I want the system to validate the insurance form fields. | so that I am alerted when any mandatory information is missing. | Medium | 3 | Complete | In Progress | Medium
103 | As a farmer. | I want to use an insurance calculator that shows the premium based on crop type, area, season, and zone. | so I can see the insurance cost before applying. | Low | 5 | In Progress | Complete | Low
104 | As a farmer. | I want to submit an insurance claim form with details like policy number, scheme name, and damage cause. | so I can request compensation for crop loss. | Medium | 3 | In Progress | Overdue
105 | As a farmer. | I want to receive confirmation messages (SMS/email) after successfully submitting an insurance application or claim, | so that I know my request was received. | High | 1 | In Progress | On Hold
106 | As a farmer. | I want to access my insurance policy details after applying. | so that I can review or track the policy when needed. | Low | 5 | In Progress
107 | As an admin. | I want to verify the documents submitted by farmers during insurance application. | so that I can ensure the authenticity of the information before approval. | Medium | 4 | Not Started
108 | As an admin. | I want to review submitted insurance claims and take necessary actions. | so that eligible farmers receive claim compensation in a timely manner. | Medium | 4 | Not Started
109 | As an admin. | I want to update the status of insurance applications and claims (e.g., approved, pending, rejected), | so that farmers can track the progress of their requests. | Low | 5 | Not Started
110 | As an admin. | I want to manage user access roles and permissions. | so that only authorized personnel can perform specific actions within the insurance system. | High | 2 | Not Started
TOTAL |  |  |  |  | 33

## Sheet2
AGILE SPRINT BACKLOG INSURANCE MODULE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #101- Fill an online insurance application form with crop and bank details.
Design the Insurance Application Form Layout |  | RanjithKumar | Completed
Implement Crop Details Form Fields |  | RanjithKumar | Completed
Implement Bank Details Form Fields |  | RanjithKumar | Completed
Integrate Form Data Validation and Submission Logic |  | RanjithKumar | Completed
User Story #102 - Validate the insurance form fields.
Validate Crop Type Input |  | RanjithKumar | Completed
Validate Crop Value and Acreage |  | RanjithKumar | Completed
Validate Bank Account Information |  | RanjithKumar | Completed
Ensure Required Fields Are Not Empty |  | RanjithKumar | Completed
User Story #103 - Insurance calculator
Develop a form to input crop type, area, season, and zone. |  | Aashik | In Progress
Create a premium calculation algorithm based on these inputs. |  | Aashik | In Progress
Display the calculated premium in a user-friendly interface. |  | Aashik | In Progress
Test and refine the calculation logic for different crop types and zones. |  | Aashik | In Progress
User Story #104 - Submitting an insurance
Design a user-friendly claim submission form with fields for policy number, scheme name, and damage cause. |  | Aashik | In Progress
Implement backend logic to save the claim data and associate it with the relevant policy. |  | Aashik | In Progress
Set up a confirmation process for submitting the form successfully. |  | Aashik | In Progress
Develop functionality to notify users of claim status updates (e.g., via email/SMS). |  | Aashik | In Progress
User Story #105 - Receiving confirmation messages
Integrate an email/SMS service for notifications. |  | Aashik | In Progress
Create message templates for different confirmation scenarios (application submission, claim status update). |  | Aashik | In Progress
Set up triggers to automatically send confirmation messages after successful form submission or status change. |  | Aashik | In Progress
Test and ensure messages are being sent promptly and correctly. |  | Aashik | In Progress
User Story #106 - Accessing insurance policy details after applying.
Build a user dashboard to display policy details. |  | Madhavan | In Progress
Integrate access control to ensure users can only view their own policy details. |  | Madhavan | In Progress
Enable a search function to locate specific policy information. |  | Madhavan | In Progress
Implement a system for displaying updates or changes in policy details. |  | Madhavan | In Progress
User Story #107 - Verifying the documents submitted by farmers during insurance application.
Develop an upload interface for farmers to submit insurance documents. |  | Madhavan | Not Started
Implement a document verification system (manual or automated) to check validity. |  | Madhavan | Not Started
Notify users of the verification status (approved, rejected). |  | Madhavan | Not Started
Create an audit trail for document submissions for transparency. |  | Madhavan | Not Started
User Story #108 - Reviewing submitted insurance claims and take necessary actions.
Create an interface for insurance agents to review submitted claims. |  | Madhavan | Not Started
Implement functionality to mark claims as approved, pending, or rejected. |  | Madhavan | Not Started
Integrate the review system with the claim history for easy tracking. |  | Madhavan | Not Started
Set up notifications to inform users of claim status changes. |  | Madhavan | Not Started
User Story #109 - Updating the status of insurance applications
Build an admin interface for updating claim or application statuses. |  | Vishweshwaran | Not Started
Implement automated triggers to notify users of status changes (approved, pending, rejected). |  | Vishweshwaran | Not Started
Ensure proper role-based access control for updating statuses. |  | Vishweshwaran | Not Started
Test the status update process to ensure consistency and accuracy. |  | Vishweshwaran | Not Started
User Story #110 - Manage user access roles and permissions.
Design a role-based access control (RBAC) system for user management. |  | Vishweshwaran | Not Started
Implement different roles with varying levels of permissions (e.g., admin, insurance agent, farmer). |  | Vishweshwaran | Not Started
Create an interface for admins to assign and manage roles. |  | Vishweshwaran | Not Started
Test role-based restrictions to ensure proper access control across the system. |  | Vishweshwaran | Not Started
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0