## Product-Backlog
PRODUCT BACKLOG INSURANCE MODULE
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
101 | As a farmer. | I want to fill an online insurance application form with my crop and bank details. | so that I can avail crop insurance under the government scheme. | High | 1 | Complete | Not Started | High
102 | As a farmer. | I want the system to validate the insurance form fields. | so that I am alerted when any mandatory information is missing. | Medium | 3 | Complete | In Progress | Medium
103 | As a farmer. | I want to use an insurance calculator that shows the premium based on crop type, area, season, and zone. | so I can see the insurance cost before applying. | Low | 5 | In Progress | Complete | Low
104 | As a farmer. | I want to submit an insurance claim form with details like policy number, scheme name, and damage cause. | so I can request compensation for crop loss. | Medium | 3 | In Progress | Overdue
105 | As a farmer. | I want to receive confirmation messages (SMS/email) after successfully submitting an insurance application or claim, | so that I know my request was received. | High | 1 | In Progress | On Hold
106 | As a farmer. | I want to access my insurance policy details after applying. | so that I can review or track the policy when needed. | Low | 5 | In Progress
107 | As an admin. | I want to verify the documents submitted by farmers during insurance application. | so that I can ensure the authenticity of the information before approval. | Medium | 4 | Not Started
108 | As an admin. | I want to review submitted insurance claims and take necessary actions. | so that eligible farmers receive claim compensation in a timely manner. | Medium | 4 | Not Started
109 | As an admin. | I want to update the status of insurance applications and claims (e.g., approved, pending, rejected), | so that farmers can track the progress of their requests. | Low | 5 | Not Started
110 | As an admin. | I want to manage user access roles and permissions. | so that only authorized personnel can perform specific actions within the insurance system. | High | 2 | Not Started
TOTAL |  |  |  |  | 33

## Sprint-Backlog
AGILE SPRINT BACKLOG INSURANCE MODULE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #101- Fill an online insurance application form with crop and bank details.
Design the Insurance Application Form Layout |  | RanjithKumar | Completed
Implement Crop Details Form Fields |  | RanjithKumar | Completed
Implement Bank Details Form Fields |  | RanjithKumar | Completed
Integrate Form Data Validation and Submission Logic |  | RanjithKumar | Completed
User Story #102 - Validate the insurance form fields.
Validate Crop Type Input |  | RanjithKumar | Completed
Validate Crop Value and Acreage |  | RanjithKumar | Completed
Validate Bank Account Information |  | RanjithKumar | Completed
Ensure Required Fields Are Not Empty |  | RanjithKumar | Completed
User Story #103 - Insurance calculator
Develop a form to input crop type, area, season, and zone. |  | Aashik | In Progress
Create a premium calculation algorithm based on these inputs. |  | Aashik | In Progress
Display the calculated premium in a user-friendly interface. |  | Aashik | In Progress
Test and refine the calculation logic for different crop types and zones. |  | Aashik | In Progress
User Story #104 - Submitting an insurance
Design a user-friendly claim submission form with fields for policy number, scheme name, and damage cause. |  | Aashik | In Progress
Implement backend logic to save the claim data and associate it with the relevant policy. |  | Aashik | In Progress
Set up a confirmation process for submitting the form successfully. |  | Aashik | In Progress
Develop functionality to notify users of claim status updates (e.g., via email/SMS). |  | Aashik | In Progress
User Story #105 - Receiving confirmation messages
Integrate an email/SMS service for notifications. |  | Aashik | In Progress
Create message templates for different confirmation scenarios (application submission, claim status update). |  | Aashik | In Progress
Set up triggers to automatically send confirmation messages after successful form submission or status change. |  | Aashik | In Progress
Test and ensure messages are being sent promptly and correctly. |  | Aashik | In Progress
User Story #106 - Accessing insurance policy details after applying.
Build a user dashboard to display policy details. |  | Madhavan | In Progress
Integrate access control to ensure users can only view their own policy details. |  | Madhavan | In Progress
Enable a search function to locate specific policy information. |  | Madhavan | In Progress
Implement a system for displaying updates or changes in policy details. |  | Madhavan | In Progress
User Story #107 - Verifying the documents submitted by farmers during insurance application.
Develop an upload interface for farmers to submit insurance documents. |  | Madhavan | Not Started
Implement a document verification system (manual or automated) to check validity. |  | Madhavan | Not Started
Notify users of the verification status (approved, rejected). |  | Madhavan | Not Started
Create an audit trail for document submissions for transparency. |  | Madhavan | Not Started
User Story #108 - Reviewing submitted insurance claims and take necessary actions.
Create an interface for insurance agents to review submitted claims. |  | Madhavan | Not Started
Implement functionality to mark claims as approved, pending, or rejected. |  | Madhavan | Not Started
Integrate the review system with the claim history for easy tracking. |  | Madhavan | Not Started
Set up notifications to inform users of claim status changes. |  | Madhavan | Not Started
User Story #109 - Updating the status of insurance applications
Build an admin interface for updating claim or application statuses. |  | Vishweshwaran | Not Started
Implement automated triggers to notify users of status changes (approved, pending, rejected). |  | Vishweshwaran | Not Started
Ensure proper role-based access control for updating statuses. |  | Vishweshwaran | Not Started
Test the status update process to ensure consistency and accuracy. |  | Vishweshwaran | Not Started
User Story #110 - Manage user access roles and permissions.
Design a role-based access control (RBAC) system for user management. |  | Vishweshwaran | Not Started
Implement different roles with varying levels of permissions (e.g., admin, insurance agent, farmer). |  | Vishweshwaran | Not Started
Create an interface for admins to assign and manage roles. |  | Vishweshwaran | Not Started
Test role-based restrictions to ensure proper access control across the system. |  | Vishweshwaran | Not Started
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## User story
S.NO | User Story | Acceptance Criteria
1 | As a farmer.want to fill an online insurance application form with my crop and bank details. so that I can avail crop insurance under the government scheme. | The form must include fields for Name, Address, and Contact Information. All mandatory fields must be filled out correctly before the form can be submitted. If any mandatory field is left blank, an error message should be displayed, prompting the user to complete the required fields.
2 | As a farmer,I want the system to validate the insurance form fields,so that I am alerted when any mandatory information is missing. | The system must identify and mark all mandatory fields in the insurance application form. The system should perform real-time validation and display error messages immediately if any mandatory field is left blank or filled incorrectly.
3 | As a farmer,I want to use an insurance calculator that shows the premium based on crop type, area, season, and zone,so I can see the insurance cost before applying. | The insurance calculator must accept inputs for crop type, area (in hectares), season, and zone. The system should calculate the premium amount based on the provided inputs using predefined rules and rates. The calculated premium amount should be displayed to the user along with detailed policy information before applying. The user should be able to review the calculated premium and policy details, and confirm to apply for the insurance by clicking the Apply button.
4 | As a farmer,I want to submit an insurance claim form with details like policy number, scheme name, and damage cause,so I can request compensation for crop loss. | The insurance claim form must include fields for policy number, scheme name, and cause of damage. All mandatory fields must be filled out correctly before the form can be submitted. If any mandatory field is left blank, an error message should be displayed, prompting the user to complete the required fields. Upon successful submission, the system should provide a confirmation message and store the claim details securely in the database.
5 | As a farmer,I want to receive confirmation messages (SMS/email) after successfully submitting an insurance application or claim,so that I know my request was received. | The system must send a confirmation message via SMS and/or email after successfully submitting an insurance application or claim. The confirmation message should include details such as the application or claim reference number and a summary of the submitted information.
6 | As a farmer, want to access my insurance policy details after applying,so that I can review or track the policy when needed. | Farmers can log in to the insurance system using their credentials. Farmers can view a dashboard displaying their insurance policy details. The dashboard includes policy number, coverage details, start and end dates, premium amount, and status. Farmers can download a copy of their insurance policy. Farmers receive notifications for any updates or changes to their policy.
7 | As an admin,I want to verify the documents submitted by farmers during insurance application,so that I can ensure the authenticity of the information before approval. | Admins can log in to the insurance system using their credentials. Admins have access to a list of pending insurance applications. Admins can view and download documents submitted by farmers. Admins can mark documents as verified or flag them for further review. Admins receive notifications for any new document submissions. The system logs all verification actions for audit purposes.
8 | As an admin,I want to review submitted insurance claims and take necessary actions,so that eligible farmers receive claim compensation in a timely manner. | Admins can log in to the insurance system using their credentials. Admins have access to a list of submitted insurance claims. Admins can view detailed information about each claim, including claim number, policy number, claim amount, and supporting documents. Admins can approve, reject, or request additional information for each claim. Admins can add comments or notes to each claim. Farmers receive notifications about the status of their claims. The system logs all actions taken on claims for audit purposes.
9 | As an admin,I want to update the status of insurance applications and claims (e.g., approved, pending, rejected),so that farmers can track the progress of their requests. | Admins can log in to the insurance system using their credentials. Admins can view a list of all insurance applications and claims. Admins can update the status of each application and claim (e.g., approved, pending, rejected). Farmers receive notifications about status updates. The updated status is reflected in the farmer's dashboard. The system logs all status updates for audit purposes.
10 | As an admin,I want to manage user access roles and permissions,so that only authorized personnel can perform specific actions within the insurance system. | Admins can log in to the insurance system using their credentials. Admins have access to a user management interface. Admins can create, update, and delete user accounts. Admins can assign roles and permissions to each user (e.g., farmer, verifier, claims processor). The system enforces role-based access control, ensuring users can only perform actions permitted by their role. The system logs all user management actions for audit purposes.

## Sprint-Review
SPRINT 1 REVIEW
REVEW REPORT
SNO. | COMMENT | PERSON RESPONSIBLE
1 | User story is not created | Ranjithkumar,Aashik Niswin ,Kaviya Sri , Vishweshwaran , Madhavan.
2 | Validation could have been done better eg phone number validation and amount for insurance | Ranjithkumar,Aashik Niswin ,Kaviya Sri , Vishweshwaran , Madhavan.
3 | Create a separate module for admin | Ranjithkumar,Aashik Niswin ,Kaviya Sri , Vishweshwaran , Madhavan.

## Sprint_Retrospective
S.no | What Went well | What went Wrong
1 | The UI looks nice | admin module has not created
2 | In User module login had been perfomed well | Segregating the user like farmer and bidder would have been done
3 | Segregating the apply insurance,calculate insurance and claim insurance is done correctly | But for claim insurance the amount should have been entered